## Sheet1
Project Completion Handover Checklist
Date:
Project:
Campus:
Building/Location:
BR Number:
Project Manager:
Principal Consultant:
Builder:
Client:
Items to be signed-off and documentation provided at the time of Practical Completion. (Items marked with * to be included in the Operations and Maintenance Manuals) | Project Manager Yes / No / Not Applicable | Eng. and Infrastructure Mgr Yes / No / Not Applicable | Operations Manager Yes / No / Not Applicable | Mgr Physical Security Yes / No / Not Applicable | Comments
Approvals
Planning Permit (if applicable)
Building Permit
Heritage Victoria Approval (if applicable)
Certificate of Practical Completion
Occupancy Permit or Certificate of Final Inspection
Consultant Statement/s of Compliance with Design Standards
Schedule of Approved Design Standards Modification Request Forms
Testing and Commissioning
Electrical
Certificate of Electrical Safety *
Independent Commissioning Agent Report
Lightning Protection Commissioning Results *
Emergency and Exit Lighting Commissioning Reports *
Renewable Energy Certificate Arrangements (if applicable)
RCD List and Test Reports *
Standby Power Commissioning Reports *
UPS Commissioning Reports *
Power Factor Device Commissioning Reports *
Hydraulic
Plumbing Compliance Certificate *
Sewer and Stormwater System CCTV Inspection
Gas Installation Compliance Certificate *
Gas Detection System Calibration Reports *
Mechanical
Equipment List (Essential and Non-Essential) *
Plantroom Logbooks and Wiring Diagrams in Place
Independent Commissioning Agent Report *
Fumehood Commissioning Reports *
BAS Commissioning Reports *
Plant Risk Assessments *
Fire/ESM
Fire Engineering Report (if applicable)
Fire Matrix
Fire and Smoke Damper Reports *
Hydrant/Hydrostatic Test Results *
Sprinkler Commissioning Reports *
Fire Detection Commissioning Reports *
Fire Wall Pentration Stopping Certificates *
Fire Door Commissioning Reports *
EWIS Commissioning Reports *
Independent Fire System Commissioning Report (if applicable)
Equipment List for Essential Services Requirements *
Evacuation Plans in Place
Fire Block Plans and Laminated A3 Detector Drawings Placed at Fire Indicator Panel
Security
Schedule of Security Equipment *
CCTV Commissioning Reports
Security System Acceptance Certification *
Handover of Keys for Cabinetry, Lockers etc
Other
Greenstar Certification
Lift (inc. chair) Design Registration *
Building Maintenance Unit Design Registration *
Pressure Vessel Design Registration *
Acoustic Commissioning Test Results (if applicable)
As-Built Information
Drawings
Draft As-Built Drawings - Architectural
Draft As-Built Drawings - Structural
Draft As-Built Drawings - Civil
Draft As-Built Drawings - Mechanical
Draft As-Built Drawings - Electrical
Draft As-Built Drawings - Hydraulic
Draft As-Built Drawings - Security
FINAL As-Built Drawings - Fire
Draft As-Built Drawings - Specialist Sub-Contractors
Specifications
Draft Specification - Architectural
Draft Specification - Structural
Draft Specification - Services
Draft Specification - Other
Manuals & Related Information
Draft Operation & Maintenance Manuals - All Trades
Contractor and Sub-Contractor Contact List
Consultant Team Contact List
Asset Register * - All Trades (Refer to Sheet 2 for Requirements)
Schedule of Outstanding DLP Identified Defects
OHS etc
Cooling Tower Registrations & Risk Management Plans
Register of Confined Spaces
Other Specific Risk Details/Locations
Details of Asbestos Removal (if applicable)
Independent Fall Protection and Arrest Certification
Material Safety Data Sheets
Maintenance Agreements and Warranties
Copies of all Maintenance Agreements in Place During Defects Liability Period
Maintenance/Service Contracts or Agreements Extending Beyond Defects Liability Period
Warranty and Guarantee Information - Design and Product
Trade Waste Agreements
Details of Specialist Cleaning Requirements
Training and Demonstrations
Pre-Handover Site Inspection Undertaken with Campus Services Staff
Fire Alarm Installation
Security and Access Control Installations
HVAC System
Building Maintenance Unit
Fire and Emergency Evacuation Procedures
Other Specialist Systems
Endorsements:
NOTE - Building is NOT to be occupied prior to receipt of the following endorsements
I certify that the information required at project handover is complete |  |  |  | Notes 1. Consultant Fees not to be fully paid until the following have been received. 2. Contract Retention Money/G'ee is not to be released until the following have been received. Drawings Final version of all drawings listed in As-Built Section above Due 4 weeks after practical completion Specifications Final version of all specifications listed in As-Built Section above Due 4 weeks after practical completion Manuals Final Version of Manuals - All Trades Due 4 weeks after practical completion
Project Manager, Project Services
Date:
Name:
Signature:
I certify that the information required at project handover is complete
Engineering and Infrastructure Manager, Campus Services (or nominee)
Date:
Name:
Signature:
I certify that the information required at project handover is complete
Operations Manager, Campus Services (or nominee)
Date:
Name:
Signature:
I certify that the information required at project handover is complete
Manager Physical Security, Campus Services (or nominee)
Date:
Name:
Signature:

## Sheet2
ASSET REGISTER REQUIREMENTS
Campus:
Building Name and Number:
Room Number or Location:
ASSET DETAILS | DEFINITION
Asset type | Brief description of the asset eg. pump
Unique descriptor | Eg. Standby pump number 2
Manufacturer | Manufacturer's name and address
Model number | Model number of the asset
Serial number | Serial number of the asset
Essential Service item | Yes/No
Compliance | Details of any requirements for non-ESM items
Asset number | Supplied by the University
INSTALLATION DETAILS
Supplier | Supplier name and address
Installation date | Date installed/acquired
Warranty details | Warranty duration and any limitations
USAGE
Size/capacity | Eg. kW, mm diameter
Power requirements | 240/415 V